## Sheet1
Risk assessment for music database application
Risk Description | Risk Assessment | Risk Severity | Risk Impact | Responsibility | Current Mitigation | Proposed Mitigation | Response | Tolerance
The database could be attacked with an SQL injection to steal data | An SQL injection would allow attackers to use malicious SQL statements to potentially steal user data such as emails and passwords. | Low | Medium | Rodion Brand | Passwords are hashed upon registration before being stored in the database this ensures a users password will not be stored in the database. The only risks are an attacker reverse engineering the hash unless the user implemented a common password that an attacker can guess. | Add code to encourage/force user to use a secure password. | Shut down and the database and utilise user emails stored in the database to inform them of a potential security breach and to advise them to update their passwords. | Tolerate
The database could be attacked with an SQL injection to delete data | An SQL injection would allow attackers to use malicious SQL statements to potentially delete the entire database. The data stored in this database is of minimal importance so while inconvenient with the appropriate measures the impact from this kind of attack can be minimised. | Low | Low | Rodion Brand | None | The database should be backed up regularly so that unauthorised modification or deletion of data can be retified. | Should the database be deleted, a new would be created with all the required tables, however there would be no data without a backup. | Tolerate
HTTP traffic is monitored by a potential attacker using wireshark or other tool | Information sent via HTTP across the cloud network can currently be intercepted due to the connection between cloud machines being insecure. A determined attacker would be able to intercept unencrypted password information between the web server and end user. | High | High | Rodion Brand | None | Use HTTPS to encrypt outgoing connections | In the unlikely event that we will notice the security breach the users would be informed via email of the breach and be advised to change their passwords | Treat
GCP Database service shuts down | Should the employed database service shut down, the website will no longer be usable. | Low | Low | GCP | None | Set up a second database to use as a backup if the main goes down | Shut down website. Attempt to restard SQL instance and contact GCP if the issue persists | Tolerate
GCP VM Instance shuts down | Should the VM on which the Flask web server runs shut down, the website will no longer be usable | Low | Low | GCP | None | Set up a second vm to use as a backup if the main goes down | Attempt to restard VM instance and contact GCP if the issue persists. Setting up a new VM and cloning the files from git is also possible | Tolerate